## ReadMe
Task:
1. Review available data. Make an assumption about plausible issue(s) with tasks flow / team performance
2. Create a forecast of expected flow state / team performance in next 6 month. Consider 3 key conditions:
- no issue exist, flow / performance remains the same;
- issue identified and removed partially;
- issue identified and mitigated to optimal state.
3. No limitations for tooling and stat. analysis methods
Context:
Small development team, use Scrum framework and typical SDLC cycle.
8 employees: 5 engineers and Scrum Master from outsourcing company, Product owner and Tech Lead from Customer. Work acceptance done by business users from Customer
Standalone application, minimal or no external dependencies, possible to do 1-2 releases every month.

## Raw data
Issue Type | Priority | Estimate (Story Points) | Key | Status | Created | Resolved | Updated | Sprint
Analysis | Medium | 5 | APP-32582 | Closed | 2022-03-08 14:10 | 2022-04-25 16:56 | 2022-04-25 17:02 | TTPQD: 2022-03-25, TTPQD: 2022-04-08
Story | Medium | 1 | APP-32453 | Closed | 2022-02-14 12:11 | 2022-03-15 09:36 | 2022-03-25 16:34 | TTPQD: 2022-02-25, TTPQD: 2022-03-11
Story | Medium | 5 | APP-32452 | Closed | 2022-02-14 12:10 | 2022-03-15 09:33 | 2022-03-15 09:33 | TTPQD: 2022-02-25, TTPQD: 2022-03-11
Story | Medium | 8 | APP-32450 | Closed | 2022-02-14 12:08 | 2022-03-15 09:05 | 2022-03-15 09:05 | TTPQD: 2022-02-25, TTPQD: 2022-03-11
Story | Medium | 3 | APP-32430 | Closed | 2022-02-10 14:14 | 2022-04-25 18:03 | 2022-04-25 18:03 | TTPQD: 2022-03-25, TTPQD: 2022-04-08
Epic | Medium |  | APP-32288 | Closed | 2022-01-25 12:38 | 2022-02-14 12:31 | 2022-02-28 11:08 | TTPQD: 2022-01-28
Story | Medium | 5 | APP-32272 | Closed | 2022-01-24 14:54 | 2022-02-08 08:54 | 2022-02-08 08:54 | TTPQD: 2022-01-28
Story | Medium | 5 | APP-32218 | Closed | 2022-01-17 13:12 | 2022-03-10 10:03 | 2022-03-10 10:03 | TTPQD: 2022-01-28, TTPQD: 2022-02-11, TTPQD: 2022-02-25
Story | Medium | 3 | APP-32139 | Closed | 2021-12-22 11:17 | 2022-02-08 08:54 | 2022-02-08 08:54 | TTPQD: 2022-01-28, TTPQD: 2022-02-11
Story | High | 1 | APP-32109 | Closed | 2021-12-16 07:30 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2022-01-14
Story | Medium | 1 | APP-32009 | Closed | 2021-12-07 16:54 | 2022-02-01 08:08 | 2022-02-01 08:08 | TTPQD: 2021-12-17
Story | Medium | 3 | APP-31991 | Closed | 2021-12-03 12:21 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2021-12-17, TTPQD: 2021-12-31
Defect | Medium | 2 | APP-31968 | Closed | 2021-11-30 14:25 | 2021-12-13 08:23 | 2021-12-13 08:23 | TTPQD: 2021-12-03
Story | Medium | 3 | APP-31945 | Closed | 2021-11-25 06:25 | 2022-02-01 07:10 | 2022-02-01 07:10 | TTPQD: 2021-12-03, TTPQD: 2021-12-17
Story | Medium | 3 | APP-31930 | Closed | 2021-11-24 09:45 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2022-01-14
Story | Medium | 5 | APP-31929 | Closed | 2021-11-24 09:42 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2022-01-14
Defect | Medium | 5 | APP-31848 | Closed | 2021-11-09 09:16 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2021-11-19, TTPQD: 2021-12-03, TTPQD: 2021-12-17, TTPQD: 2021-12-31, TTPQD: 2022-01-14
Defect | Low | 5 | APP-31835 | Closed | 2021-11-05 16:42 | 2022-03-08 11:21 | 2022-03-09 09:35 | TTPQD: 2021-12-03, TTPQD: 2021-12-17, TTPQD: 2021-12-31
Story | Medium | 3 | APP-31783 | Closed | 2021-11-02 14:10 | 2022-01-26 08:19 | 2022-01-26 08:19 | TTPQD: 2021-11-05, TTPQD: 2021-11-19, TTPQD: 2021-12-17, TTPQD: 2021-12-31, TTPQD: 2022-01-14
Story | Medium | 5 | APP-31770 | Closed | 2021-11-01 15:30 | 2022-03-01 10:29 | 2022-03-01 10:29 | TTPQD: 2022-02-11, TTPQD: 2022-02-25, TTPQD: 2022-03-11
Defect | Medium | 8 | APP-31699 | Closed | 2021-10-20 08:23 | 2021-10-27 10:55 | 2021-10-27 10:57 | TTPQD: 2021-10-22, TTPQD: 2021-11-05
Defect | High | 5 | APP-31698 | Closed | 2021-10-20 07:38 | 2021-10-27 10:30 | 2021-10-27 10:30 | TTPQD: 2021-10-22, TTPQD: 2021-11-05
Defect | Medium | 2 | APP-31676 | Closed | 2021-10-18 11:56 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2021-11-19, TTPQD: 2021-12-03, TTPQD: 2021-12-17
Defect | Medium | 13 | APP-31613 | Closed | 2021-10-06 09:34 | 2021-12-13 08:23 | 2021-12-13 08:23 | TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19
Defect | Medium | 1 | APP-31588 | Closed | 2021-10-04 13:20 | 2021-11-22 09:16 | 2021-11-22 09:16 | TTPQD: 2021-10-08, TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19
Story | Medium | 5 | APP-31577 | Closed | 2021-09-30 07:37 | 2022-01-26 08:19 | 2022-01-26 08:19 | TTPQD: 2021-10-08, TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19, TTPQD: 2021-12-03, TTPQD: 2021-12-17, TTPQD: 2021-12-31, TTPQD: 2022-01-14
Story | Medium | 8 | APP-31565 | Closed | 2021-09-28 12:55 | 2021-10-27 10:34 | 2021-10-27 10:34 | TTPQD: 2021-10-08
Story | Medium | 2 | APP-31559 | Closed | 2021-09-27 14:33 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2021-12-03, TTPQD: 2021-12-17
Defect | Medium | 8 | APP-31555 | Closed | 2021-09-27 12:48 | 2021-12-13 08:23 | 2021-12-13 08:23 | TTPQD: 2021-10-08, TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19
Story | Medium | 5 | APP-31548 | Closed | 2021-09-24 09:46 | 2021-10-04 11:20 | 2021-10-04 11:20 | TTPQD: 2021-08-27, TTPQD: 2021-09-10, TTPQD: 2021-09-24, TTPQD: 2021-10-08
Defect | Medium | 5 | APP-31529 | Closed | 2021-09-21 11:16 | 2021-10-04 11:20 | 2021-10-04 11:20 | TTPQD: 2021-09-24, TTPQD: 2021-10-08
Defect | Medium | 5 | APP-31524 | Closed | 2021-09-20 14:01 | 2021-10-15 07:58 | 2021-10-15 07:58 | TTPQD: 2021-10-08
Technical Improvement | Medium | 8 | APP-31480 | Closed | 2021-09-13 12:38 | 2021-10-12 10:01 | 2021-10-12 10:01 | TTPQD: 2021-09-24, TTPQD: 2021-10-08
Story | Medium | 3 | APP-31464 | Closed | 2021-09-10 08:34 | 2021-10-15 07:58 | 2021-10-15 07:58 | TTPQD: 2021-09-24, TTPQD: 2021-10-08, TTPQD: 2021-10-22
Story | Medium | 5 | APP-31405 | Closed | 2021-09-06 06:55 | 2021-11-03 07:07 | 2021-11-03 07:07 | TTPQD: 2021-09-10, TTPQD: 2021-09-24, TTPQD: 2021-10-08, TTPQD: 2021-10-22, TTPQD: 2021-11-05
Defect | Medium | 5 | APP-31338 | Closed | 2021-08-24 09:29 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19, TTPQD: 2021-12-03, TTPQD: 2021-12-17
Defect | Medium | 2 | APP-31283 | Closed | 2021-08-12 13:37 | 2021-12-13 08:23 | 2021-12-13 08:23 | TTPQD: 2021-09-10, TTPQD: 2021-09-24, TTPQD: 2021-10-08, TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19
Story | Medium | 8 | APP-30923 | Closed | 2021-06-23 16:02 | 2021-11-03 10:44 | 2021-11-03 10:44 | TTPQD: 2021-08-13, TTPQD: 2021-08-27, TTPQD: 2021-09-10, TTPQD: 2021-09-24, TTPQD: 2021-10-08
Story | Medium | 5 | APP-30922 | Closed | 2021-06-23 15:57 | 2021-11-03 10:44 | 2021-11-03 17:50 | TTPQD: 2021-08-13, TTPQD: 2021-08-27, TTPQD: 2021-09-10, TTPQD: 2021-09-24, TTPQD: 2021-10-08
Story | Medium | 1 | APP-30576 | Closed | 2021-05-12 09:29 | 2022-03-08 11:21 | 2022-03-08 11:21 | TTPQD: 2021-06-18, TTPQD: 2021-07-02, TTPQD: 2021-07-16, TTPQD: 2021-08-13, TTPQD: 2021-08-27, TTPQD: 2021-09-10, TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19, TTPQD: 2021-12-03, TTPQD: 2021-12-17, TTPQD: 2021-12-31, TTPQD: 2022-01-14
Story | Medium | 8 | APP-30190 | Closed | 2021-03-19 14:34 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2021-08-13, TTPQD: 2021-08-27, TTPQD: 2021-09-10, TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19, TTPQD: 2021-12-03, TTPQD: 2021-12-17, TTPQD: 2021-12-31
Story | Medium | 5 | APP-30176 | Closed | 2021-03-17 13:13 | 2022-03-08 11:20 | 2022-03-08 11:20 | TTPQD: 2021-07-16, TTPQD: 2021-08-13, TTPQD: 2021-08-27, TTPQD: 2021-09-10, TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19, TTPQD: 2021-12-03, TTPQD: 2021-12-17
Story | Medium | 1 | APP-30149 | Closed | 2021-03-12 13:18 | 2021-12-13 08:23 | 2021-12-13 08:23 | TTPQD: 2021-12-03
Story | Medium | 5 | APP-29874 | Closed | 2021-02-11 15:35 | 2021-12-13 08:23 | 2021-12-13 08:23 | TTPQD: 2021-07-30, TTPQD: 2021-08-13, TTPQD: 2021-08-27, TTPQD: 2021-09-10, TTPQD: 2021-10-22, TTPQD: 2021-11-05, TTPQD: 2021-11-19

## Jira Reports
Time in status summary
| In development | In Peer review | In Testing | In User Acceptance | Ready for Release
Average | 1w 4d 6h | 2w 2d 18h | 1d 21h | 2d 11h | 2w 1d 22h
Median | 5d 23h | 1w 1d 1h | 10h 55min | 10h 55min | 6d 4h
In development
In Peer review
In Testing
In User Acceptance (Ready for UAT, In UAT)
Ready for Release